## GESPROY - Burndown
GESTIÓN DE PROYECTOS SPRINT 1 - BURNDOWN CHART
| ID Tarea | Tareas |  | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27
|  |  | PH Estimado | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7 | Dia 8 | Dia 9 | Dia 10
| 1 | Creación de las Clases de Diseño | 5 | 2019-05-21: 1; 2019-05-22: 1; 2019-05-23: 1; 2019-05-24: 2
| 2 | Realización de Diagrama de Secuencia Camino Básico | 5 | bar: 2019-05-22 to 2019-05-24
| 3 | Mostrar listado de proyectos seleccionados | 20 | 2019-05-22: 2; 2019-05-23: 3; 2019-05-24: 3
| 4 | Creación de ficheros de datos json | 10 | 2019-05-22: 1; 2019-05-23: 2; 2019-05-24: 2
| 5 | Implementación Clases de Diseño, serializar y deserializar fichero. | 20 | 2019-05-22: 2; 2019-05-23: 4; 2019-05-24: 4
|  | Esfuerzo restante | 60 | 60 | 53 | 41 | 31 | 24 | 30 | 24 | 18
|  | Tendencia Ideal | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12
Note on E5: Coria: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on F8: Coria: Use a negative number to indicate that the level of effort just went up during your Sprint.
Note on H9: Coria: Use a negative number to indicate that the level of effort just went up during your Sprint.
Note on J9: Coria: Use a positive number to indicate that the item is complete.
Note on I10: Coria: Use a negative number to indicate that your level of effort just went up.
Note on M10: Coria: Use this formatting to indicate that you are projecting a number that is not yet final.